## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Central Mechanical | HARISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15319 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Harishnapur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000721/2023-2024 | 4032/CMD | 29/08/2023 | 28/09/2023 | SUBRATA BHADRA | 28.96 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | HARISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15319 | New | Material Requisition To Resource Division |  |  | RTOR000275/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 8.85 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-I | Burdwan Division | HARISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15319 | New | Material Requisition To Resource Division |  |  | RTOR000481/2023-2024 | 4005/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 10.43 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Burdwan Division | HARISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15319 | New | Material Requisition To Resource Division |  |  | RTOR000670/2023-2024 | 5084/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-I | Central Mechanical | HARISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15319 | New | New service connection charges for Harishnapur PWSS TW-01 |  |  | BILL/02411/2023-2024 | BP-2023-24-495 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.92 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-I | Central Mechanical | HARISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15319 | New | New Service connection at HARISHNAPUR, PWSS. |  |  | BILL/02358/2023-2024 | BP-2023-24-483 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-I | Burdwan Division | HARISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15319 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000388/2023-2024 | 3197/BWD | 24/07/2023 | 16/01/2026 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 51.36 | 4.14 | 55
8 | PURBA BARDHAMAN | Raina-I | Central Mechanical | HARISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15319 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
Total | [13 empty] | 1392.6 | 51.36 | 3.69