## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Narottambati Piped Water Supply Scheme | SM/15486 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] |  |  | ORD/000845/2023-2024 | 1759/BSD | 28/07/2023 | 02/10/2023 | MD HASIN | 0.85 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Narottambati Piped Water Supply Scheme | SM/15486 | New | Material Requisition To Resource Division |  |  | RTOR000352/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 11.94 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Narottambati Piped Water Supply Scheme | SM/15486 | New | Material Requisition To Resource Division |  |  | RTOR000681/2023-2024 | 5081/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Narottambati Piped Water Supply Scheme | SM/15486 | New | Material Requisition To Resource Division |  |  | RTOR000425/2023-2024 | 3837/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 6.91 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Narottambati Piped Water Supply Scheme | SM/15486 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Narottambati Piped Water Supply Scheme | SM/15486 | New | New service connection for Narottambati PWSS. |  |  | BILL/02404/2023-2024 | BP-2023-24-496 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.09 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Narottambati Piped Water Supply Scheme | SM/15486 | New | NEW SERVICE CONNECTION FOR NAROTTAMBATI PWSS TW 2. |  |  | BILL/03180/2023-2024 | BP-2023-24-664 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.31 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Narottambati Piped Water Supply Scheme | SM/15486 | New | NAROTTAMBATI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000488/2023-2024 | 3501/BWD | 10/08/2023 | 01/01/2026 | S.S.S. ENTERPRISES | 585.33 | 0 | 0 | 75
9 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Narottambati Piped Water Supply Scheme | SM/15486 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-12-2024 to 28-02-2025 |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001043/2024-2025 | 2636/BSD | 29/11/2024 | 27/02/2025 | SK. ASFIA | 1.2 | 0 | 0 | 60
10 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Narottambati Piped Water Supply Scheme | SM/15486 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Narottombati Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000909/2023-2024 | 4173/CMD | 29/08/2023 | 28/09/2023 | J.S. CONSTRUCTION. | 29.71 | 0 | 0 | 90
Total | [13 empty] | 760.19 | 0 | 0