## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gangpur Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000670/2023-2024 | 4008/CMD | 29/08/2023 | 28/09/2023 | CHATTERJEE ENTERPRISE | 28.95 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 6.43 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | Material Requisition To Resource Division |  |  | RTOR000401/2023-2024 | 3873/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 5.75 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | Material Requisition To Resource Division |  |  | RTOR000255/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 4.55 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | Material Requisition To Resource Division |  |  | RTOR000566/2023-2024 | 4920/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 42.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 4112/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 15.69 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | NEW SERVICE CONNECTION FOR GANGPUR TW 1. |  |  | BILL/02953/2023-2024 | BP-2023-24-636 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.74 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | Quotation for new service connection Gangpur PWSS TW-2. |  |  | BILL/00322/2024-2025 | BP-2024-25-163 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.72 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALGANA & GANGPUR Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000538/2023-2024 | 3699/BWD | 24/08/2023 | 01/10/2025 | SUPRITI ENTERPRISE | 1345.79 | 0 | 0 | 20
10 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME | SM/15487 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
Total | [13 empty] | 1514.23 | 0 | 0