## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | Material Requisition To Resource Division |  |  | RTOR000417/2023-2024 | 3865/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 20.78 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | Material Requisition To Resource Division |  |  | RTOR000371/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 3.55 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | Material Requisition To Resource Division |  |  | RTOR000687/2023-2024 | 5078/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | Continuation Order- Hiring of inspection vehicle (Diesel /CNG/LPG Driven) for supervision of site for the office of Assistant Engineer under CMD,PHE,Dte. [W.E.F-30.04.2024 to 28.06.2024 ] | ASSISTANT ENGINEER | Junior Engineer | ORD/000423/2024-2025 | 703/CMSD | 29/04/2024 | 28/06/2024 | SUBRATA BHADRA | 0.79 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-06-2024 to 31-08-2024" |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000228/2024-2025 | 918/BSD | 28/05/2024 | 28/08/2024 | SK. ASFIA | 1.2 | 0.4 | 33.2 | 60
6 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | New electric connection for Pipuldaha PWSS. |  |  | BILL/01868/2023-2024 | BP-2023-24-346 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.54 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | New electric connection for Pipuldaha PWSS, PH-1. |  |  | BILL/01883/2023-2024 | BP-2023-24-345 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.76 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | PIPULDAHA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000458/2023-2024 | 3440/BWD | 08/08/2023 | 01/07/2026 | SK ABDUL HALIM | 644.77 | 289.73 | 44.94 | 97
10 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Pipuldaha Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000728/2023-2024 | 4039/CMD | 29/08/2023 | 28/09/2023 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 28.94 | 11.65 | 40.25 | 50
11 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Pipuldaha Piped Water Supply Scheme | SM/15488 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2024 to 31-01-2025) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000896/2024-2025 | 2438/BSD | 29/10/2024 | 03/01/2025 | PARVIN BEGAM | 0.85 | 0.56 | 66.67 | 100
Total | [13 empty] | 821.05 | 302.34 | 36.82