## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Material Requisition To Resource Division |  |  | RTOR000419/2023-2024 | 3863/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 3.95 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Material Requisition To Resource Division |  |  | RTOR000303/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.3 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Material Requisition To Resource Division |  |  | RTOR000662/2023-2024 | 5082/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 30-11-2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000682/2024-2025 | 1957/BSD | 30/08/2024 | 29/11/2024 | SK. ASFIA | 1.2 | 0 | 0 | 60
5 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Chaudanga Piped Water Supply Scheme | SM/15489 | New | New electric connection for Chaudanga PWSS, PH-1. |  |  | BILL/01884/2023-2024 | BP-2023-24-347 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.67 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Chaudanga Piped Water Supply Scheme | SM/15489 | New | New electric connection for Chuadanga PWSS, PH-2. |  |  | BILL/01885/2023-2024 | BP-2023-24-348 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARABAINAN & CHAUDANGA Piped Water Supply Scheme under Raina ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000412/2023-2024 | 3257/BWD | 27/07/2023 | 11/10/2025 | SK ALIM | 1144.16 | 0 | 0 | 90
9 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAUDANGA Water Supply Scheme [ Block-RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000805/2023-2024 | 4090/CMD | 29/08/2023 | 30/04/2025 | MS DAS ELECTRIC CO | 28.98 | 0 | 0 | 50
Total | [13 empty] | 1306.26 | 0 | 0