## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME | SM/15555 | Augmentation | Yard lighting arrangement & allied works at Panuhat water supply scheme under Katwa-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000464/2024-2025 | 2791/CMD | 01/10/2024 | 30/11/2024 | BEHERA ENTERPRISE | 7.11 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME | SM/15555 | Augmentation | NEW SERVICE CONNECTION FOR ADDITIONAL TUBE WELL AT PANUHAT |  |  | BILL/00128/2024-2025 | BP-2024-25-62 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.52 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME | SM/15555 | Augmentation | Quotation for new service connection at Augmentation of Panuhat PWSS TW - 01. |  |  | BILL/00749/2024-2025 | BP-2024-25-283 | 10/09/2024 | 10/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.98 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME | SM/15555 | Augmentation | Construction of Pump House, Boundary walls and Raising Main for Aug. of PANUHAT Piped W/S. Scheme under Katwa-I Block, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000923/2023-2024 | 5484/BWD | 13/12/2023 | 11/02/2024 | SUBODH KUMAR MONDAL | 9.73 | 2.16 | 22.2 | 26
Total | [13 empty] | 26.35 | 2.16 | 8.2