## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME | SM/15556 | Augmentation | Route Survey & Preparation of DPR for RAYAN PART-(IV) DURGA DANGA W/S Scheme under Burdwan-I Block under Burdwan Sub- Division under Burdwan Division PHE Dte |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000851/2024-2025 | 2587/BSD | 26/11/2024 | 10/01/2025 | APEX ENGINEERING | 2.43 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME | SM/15556 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 4102/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 10.19 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME | SM/15556 | Augmentation | Quotation for new service connection of Rayan (Aug) Part-4 (Durgadanga) PWSS TW 1 |  |  | BILL/00443/2024-2025 | BP-2024-25-236 | 30/07/2024 | 30/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.91 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME | SM/15556 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rayan. Part -4 Durgadanga Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000095/2023-2024 | 2597/CMD | 07/06/2023 | 30/04/2025 | M/S, S.S. ENTERPRISE. | 24.11 | 0 | 0 | 50
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME | SM/15556 | Augmentation | Augmentation RAYAN (Part-IV) (Durgadanga) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of switch rooms & boundary walls with gates at different TW site under Burdwan - I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000994/2023-2024 | 245/BWD | 15/01/2024 | 01/04/2025 | DHIRENDRANATH SOM | 93.34 | 0 | 0 | 100
Total | [13 empty] | 135.97 | 0 | 0