## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME | SM/15557 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Srikhanda Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000087/2023-2024 | 2582/CMD | 07/06/2023 | 07/01/2025 | AMUSAR IMPEX PVT. LTD. | 11.25 | 0 | 0 | 95
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME | SM/15557 | Augmentation | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Nanagar PWSS, Srikhanda PWSS, under KATWA -I Block under Katwa Sub-Divn under Burdwan Division, PHE Dte. District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000685/2024-2025 | 3655/BWD | 21/10/2024 | 18/02/2025 | HAMID SK | 121.69 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME | SM/15557 | Augmentation | Quotation for new service connection at Augmentation of Srikhanda PWSS, PH-1. |  |  | BILL/00464/2024-2025 | BP-2024-25-249 | 01/08/2024 | 01/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.73 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME | SM/15557 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT AUGMENTATION OF SRIKHANDA PWSS TW 2 |  |  | BILL/00365/2024-2025 | BP-2024-25-188 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.98 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME | SM/15557 | Augmentation | Augmentation of SRIKHANDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000489/2023-2024 | 3508/BWD | 10/08/2023 | 01/01/2026 | GUPTA ENTERPRISE | 656.48 | 252.17 | 38.41 | 18
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME | SM/15557 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 2 at Augumentation of Srikhanda Water Supply Scheme [ BLOCK- Katwa-I ]under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001644/2023-2024 | 1626/CMD | 15/03/2024 | 14/04/2024 | D.K. ELECTRIC | 11.62 | 10.52 | 90.5 | 88
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME | SM/15557 | Augmentation | Construction of Pump House, Boundary walls and Raising Main for Aug. of SRIKHANDA Piped Water Supply Scheme under Katwa-I Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000924/2023-2024 | 5486/BWD | 13/12/2023 | 07/01/2025 | BABUL SK | 9.77 | 0 | 0 | 75
Total | [13 empty] | 819.53 | 262.69 | 32.05