## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION BHALKI Z-I & Z-II PWSS | SM/15560 | Augmentation | New service connection charges for Bhalki PWSS TW-1 |  |  | BILL/00786/2024-2025 | BP-2024-25-298 | 17/09/2024 | 17/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.63 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION BHALKI Z-I & Z-II PWSS | SM/15560 | Augmentation | Quotation for new service connection at Bhalki Zone-I/Zone-II, Aug-1. PWSS |  |  | BILL/00897/2024-2025 | BP-2024-25-337 | 04/10/2024 | 04/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.77 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION BHALKI Z-I & Z-II PWSS | SM/15560 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of BHALKI (ZONE-I & II) [AUSGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001088/2023-2024 | 4510/CMD | 06/10/2023 | 01/10/2025 | C.M. ENTERPRISE | 24.42 | 0 | 0 | 50
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION BHALKI Z-I & Z-II PWSS | SM/15560 | Augmentation | Aug. of BHALKI ZONE-I Piped Water Supply Scheme with Rising Main & Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation at Headwork TW site under Ausgram-II Block, District:- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001014/2023-2024 | 474/BWD | 05/02/2024 | 29/06/2025 | SK AFJAL RAHAMAN | 114.56 | 0 | 0 | 25
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION BHALKI Z-I & Z-II PWSS | SM/15560 | Augmentation | Aug. of BHALKI ZONE-II Piped Water Supply Scheme with Rising Main & Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation at Headwork TW site under Ausgram-II Block, District:- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001022/2023-2024 | 568/BWD | 08/02/2024 | 02/02/2025 | SK ABDUL LALAN | 74.12 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION BHALKI Z-I & Z-II PWSS | SM/15560 | Augmentation | Source Augmentation of BHALKI Zone-I & Zone-II Piped Water Supply Scheme [Tube Well, Pump House, Boundary Wall, Rising Main, FHTC, etc.], Block-Ausgram-II, Dist.- Purba Bardhaman, under Burdwan Division P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000104/2023-2024 | 2273/BWD | 18/05/2023 | 30/04/2025 | S.R. ENTERPRISE | 92.2 | 0 | 0 | 40
Total | [13 empty] | 312.7 | 0 | 0