## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME | SM/15562 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme KASHIARA PWSS (Sl No-5) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000073/2023-2024 | 397/KTS | 13/04/2023 | 13/05/2023 | SIRCON ENGINEERING SERVICES | 2.62 | 2.62 | 100 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME | SM/15562 | Augmentation | Augmentation of KASHIARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under MONGALKOTE Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000753/2023-2024 | 4666/BWD | 01/11/2023 | 01/01/2025 | M/S B. RAI CONSTRUCTION COMPANY | 372.35 | 103.98 | 27.92 | 30
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME | SM/15562 | Augmentation | Yard lighting arrangement & allied works at Kasiara water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000409/2024-2025 | 2789/CMD | 01/10/2024 | 30/11/2024 | BABA MALLESHWAR ENTERPRISE. | 5.55 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME | SM/15562 | Augmentation | Quotation for new service connection at Augmentation of Kashiara PWSS TW-1 |  |  | BILL/01088/2024-2025 | BP-2024-25-398 | 22/11/2024 | 22/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0 | 0
Total | [13 empty] | 384.26 | 106.59 | 27.74