## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI | SM/15565 | Augmentation | Construction of Boundary wall at Head Works Site of LOHAI Water Supply scheme under RAINA-II Block of Burdwan Division, PHE Dte. (Length -190.00 Mtr, Col-60 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000078/2023-2024 | 2053/BWD | 04/05/2023 | 03/07/2023 | S. MITRA & CO. | 20.43 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI | SM/15565 | Augmentation | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of LOHAI Piped Water Supply Scheme within Raina II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000149/2023-2024 | 2422/BWD | 30/05/2023 | 29/06/2023 | JAI MAA DURGA & CO. | 19.37 | 5.31 | 27.41 | 50
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI | SM/15565 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Lohai Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000086/2023-2024 | 2592/CMD | 07/06/2023 | 07/07/2023 | SOUVIK HALDER | 11.36 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI | SM/15565 | Augmentation | Preparation and Submission of DPR for Augmentation of Lohai PWSS under Raina-II Development Block under Burdwan Division, P.H.E Dte (2nd Call) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001225/2023-2024 | 2973/BSD | 20/12/2023 | 04/01/2024 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI | SM/15565 | Augmentation | Making illumination arrangement and mise works at LOHAI water supply scheme RAINA-II BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000471/2024-2025 | 2953/CMD | 20/11/2024 | 19/01/2025 | M/S GHOSH ENTERPRISE | 9.84 | 0 | 0 | 60
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI | SM/15565 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Lohai village of Raina-II Block under Lohai Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000519/2025-2026 | 1194/BSD | 22/05/2025 | 01/06/2025 | AIRC CONSTRUCTION (OPC) PVT. LTD. | 0.73 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI | SM/15565 | Augmentation | Inter connection of pump at Bhanjapur including laying of pipe line due to widening of road & connection of pipe line to the higher dia. of LOHAI Piped Water Supply Scheme and its adjoining mouzas within RAINA-II BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001067/2024-2025 | 357/BWD | 16/01/2025 | 12/04/2025 | ISHAN CONSTRUCTION | 7.07 | 0 | 0 | 95
Total | [13 empty] | 69.58 | 6.09 | 8.75