## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | SM/15568 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Berawa Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000101/2023-2024 | 2600/CMD | 07/06/2023 | 01/07/2025 | SOUNAK ENTERPRISE | 22.6 | 0 | 0 | 50
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | SM/15568 | Augmentation | Augmentation of BERWA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000587/2023-2024 | 3743/BWD | 28/08/2023 | 27/03/2026 | ROY ENTERPRISE | 334.82 | 132.35 | 39.53 | 65
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | SM/15568 | Augmentation | Illumination arrangement & different electro-mechanical works at BARWA water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000443/2024-2025 | 2796/CMD | 01/10/2024 | 30/11/2024 | A.K. ENTERPRISE | 11.65 | 0 | 0 | 60
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | SM/15568 | Augmentation | Replacement of Tube-well & Rising main at Head work TW site for BARWA Piped Water Supply Scheme under MEMARI-II Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000226/2024-2025 | 2523/BWD | 03/07/2024 | 01/10/2024 | ROY ENTERPRISE | 15.27 | 12.14 | 79.47 | 80
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | SM/15568 | Augmentation | Withdrawing damaged p/m set from defunct tube well and Supply & Installation of submersible pumping machinery for T.W. No.-I (Replacement tube well) and different electro-mechanical works for P.H No.-I & II at BARWA w/s scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000460/2024-2025 | 1147/CMSD | 02/09/2024 | 02/10/2024 | MITRA ENTERPRISE | 4.16 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | SM/15568 | Augmentation | NEW SERVICE CONNECTION FOR AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME. |  |  | BILL/02827/2023-2024 | BP-2023-24-594 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.25 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | SM/15568 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 03/07/2025 | PROJECT INDIA | 394.29 | 0 | 0 | 0
Total | [13 empty] | 790.05 | 144.49 | 18.29