## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SUDPUR PIPED WATER SUPPLY SCHEME | SM/15573 | Augmentation | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000486/2024-2025 | 3141/BWD | 20/08/2024 | 18/12/2024 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 0 | 50
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SUDPUR PIPED WATER SUPPLY SCHEME | SM/15573 | Augmentation | Augmentation of SUDPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman._2ND CALL | Assistant Engineer | JE RWS | ORD/000658/2023-2024 | 4122/BWD | 14/09/2023 | 01/01/2026 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 442.27 | 0 | 0 | 63
Total | [13 empty] | 568.56 | 0 | 0