## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Material Requisition To Resource Division |  |  | RTOR000109/2022-2023 | 1642/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 1.83 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 1261/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 7.73 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Material Requisition To Resource Division |  |  | RTOR000621/2023-2024 | 4879/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 31.56 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/000442/2024-2025 | 306/AE/HQ | 31/05/2024 | 31/07/2024 | MD HASIN | 0.8 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | AE(HQs) | Contractual Junior Engineer | ORD/000707/2024-2025 | 802/AE/HQ | 30/09/2024 | 30/11/2024 | MD HASIN | 0.8 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | AE(HQs) | Contractual Junior Engineer | ORD/000507/2024-2025 | 547/AE/HQ | 01/08/2024 | 01/10/2024 | MD HASIN | 0.8 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001205/2023-2024 | 43/AE/HQ | 29/01/2024 | 29/03/2024 | MD HASIN | 0.8 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Different work for MERA PWSS (Mustafapur, Arangabad and Mera mouza) plinth protection for pump house & OHR under MERA PWSS, at Katwa -I Block under Katwa Sub-Division under Burdwan Division PHE Dte. | Assistant Engineer |  | ORD/000964/2024-2025 | 4374/BWD | 13/12/2024 | 13/03/2025 | J.K. CORPORATION | 51.3 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001231/2023-2024 | 236/AE/HQ | 28/03/2024 | 28/05/2024 | MD HASIN | 0.8 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MERA Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000886/2023-2024 | 4149/CMD | 29/08/2023 | 28/09/2023 | GOENKA ENTERPRISE | 26.98 | 0 | 0 | 91
12 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | New service connection for MERA PWSS TW 2. |  |  | BILL/02446/2023-2024 | BP-2023-24-525 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.08 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | New Service connection for Mera PWSS TW-1 |  |  | BILL/02351/2023-2024 | BP-2023-24-462 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.98 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | AE(HQs) | Contractual Junior Engineer | ORD/000897/2024-2025 | 1010/AE/HQ | 29/11/2024 | 29/01/2025 | MD HASIN | 0.8 | 0 | 0 | 0
15 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | AE(HQs) | Contractual Junior Engineer | ORD/001154/2024-2025 | 186/AE/HQ | 31/01/2025 | 31/03/2025 | MD HASIN | 0.8 | 0 | 0 | 0
16 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME | SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.10.2025 to 30.11.2025] | AE(HQs), Burdwan Division, PHE Dte. | Contractual Junior Engineer | ORD/000701/2025-2026 | 1195/AE/HQ | 24/09/2025 | 24/11/2025 | MD HASIN | 0.8 | 0 | 0 | 0
Total | [13 empty] | 189 | 0 | 0