## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. | SM/15581 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 10.04 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. | SM/15581 | New | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 10.94 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. | SM/15581 | New | New service connection charges for Bara Baharkuli PWSS TW-2 |  |  | BILL/01668/2023-2024 | BP-2023-24-219 | 10/11/2023 | 10/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.15 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. | SM/15581 | New | BARA BAHARKULI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000178/2023-2024 | 2597/BWD | 02/06/2023 | 01/06/2024 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 236.3 | 145.52 | 61.58 | 65
5 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. | SM/15581 | New | Material Requisition To Resource Division |  |  | RTOR000785/2023-2024 | 328/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 24.62 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. | SM/15581 | New | Quotation for new electric service connection at Bara Baharkhuli PH NO.-1 |  |  | BILL/01747/2023-2024 | BP-2023-24-268 | 11/12/2023 | 11/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.87 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. | SM/15581 | New | Restoration work of Barabaharkuli to Badla village road with a bridge over river Behula road from 0.0 km to 1.3 km and 1.8 km to 2.2 km damadged due to laying of underground water pipeline by PHE with box cutting and jhama with moorum consolidation under kalna highway subdivision of Burdwan south highway division ,P.W(Roads)dte ,during the year 2023-2024 |  |  | BILL/00645/2024-2025 | 825/JJM | 13/09/2024 | 13/09/2024 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.36 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. | SM/15581 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
Total | [13 empty] | 979.58 | 145.52 | 14.86