## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHAKDAHA PIPED WATER SUPPLY SCHEME | SM/15582 | New | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 4.39 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHAKDAHA PIPED WATER SUPPLY SCHEME | SM/15582 | New | Material Requisition To Resource Division |  |  | RTOR000397/2023-2024 | 3843/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 1.09 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHAKDAHA PIPED WATER SUPPLY SCHEME | SM/15582 | New | Material Requisition To Resource Division |  |  | RTOR000581/2023-2024 | 4895/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 4.76 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHAKDAHA PIPED WATER SUPPLY SCHEME | SM/15582 | New | CHAKDAHA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000080/2023-2024 | 2071/BWD | 04/05/2023 | 01/09/2023 | CHAKRABORTY PROJECTS | 85.35 | 0 | 0 | 76
5 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | CHAKDAHA PIPED WATER SUPPLY SCHEME | SM/15582 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | CHAKDAHA PIPED WATER SUPPLY SCHEME | SM/15582 | New | New service connection charges for Chakdaha PWSS TW-1 |  |  | BILL/01765/2023-2024 | BP-2023-24-279 | 21/12/2023 | 21/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.1 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | CHAKDAHA PIPED WATER SUPPLY SCHEME | SM/15582 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at CHAKDAHA [KETUGRAM-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000890/2023-2024 | 4153/CMD | 29/08/2023 | 30/05/2025 | AMUSAR IMPEX PVT. LTD. | 21.26 | 0 | 0 | 47
8 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHAKDAHA PIPED WATER SUPPLY SCHEME | SM/15582 | New | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 31/08/2025 | M/S M.M. ENTERPRISE | 205.15 | 0 | 0 | 65
Total | [13 empty] | 408.38 | 0 | 0