## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME | SM/15585 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000639/2023-2024 | 3957/BWD | 07/09/2023 | 24/07/2026 | M/S B. NANDI | 758.52 | 146.35 | 19.29 | 20
2 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | SHYAMPUR PIPE WATER SUPPLY SCHEME | SM/15585 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at SHYAMPUR [PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000888/2023-2024 | 4151/CMD | 29/08/2023 | 01/04/2025 | DUTTA ENTERPRISE | 20.8 | 0 | 0 | 100
3 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME | SM/15585 | New | Material Requisition To Resource Division |  |  | RTOR000320/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 14.98 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME | SM/15585 | New | Material Requisition To Resource Division |  |  | RTOR000547/2023-2024 | 4300/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 0.58 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME | SM/15585 | New | Material Requisition To Resource Division |  |  | RTOR000589/2023-2024 | 4946/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 9.76 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | SHYAMPUR PIPE WATER SUPPLY SCHEME | SM/15585 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 23/02/2025 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME | SM/15585 | New | CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR SHYAMPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000570/2024-2025 | 1016/KSD | 07/08/2024 | 22/08/2024 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 99.69 | 100
8 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | SHYAMPUR PIPE WATER SUPPLY SCHEME | SM/15585 | New | Quotation for new service connection at Shyampur PWSS PH-2. |  |  | BILL/00458/2024-2025 | BP-2024-25-250 | 01/08/2024 | 01/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.61 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | SHYAMPUR PIPE WATER SUPPLY SCHEME | SM/15585 | New | Quotation for new service connection at Shyampur PWSS PH 1. |  |  | BILL/00934/2024-2025 | BP-2024-25-352 | 05/10/2024 | 05/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.57 | 0 | 0 | 0
Total | [13 empty] | 873.73 | 147.01 | 16.83