## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 8.53 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 9.27 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR CHAKSIMLA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001151/2023-2024 | 2020/KSD | 06/03/2024 | 16/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 99.78 | 2
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | Material Requisition To Resource Division |  |  | RTOR000793/2023-2024 | 318/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 30.81 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | New service connection at Chak Shimla PWSS Ph-1 |  |  | BILL/02323/2023-2024 | BP-2023-24-449 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.74 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | New service connection at Chak Shimla PWSS Ph-2 |  |  | BILL/02324/2023-2024 | BP-2023-24-450 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.35 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALINDAR, CHAK SHIMLA & DWARIATAN Piped Water Supply Scheme under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000539/2023-2024 | 3700/BWD | 24/08/2023 | 02/10/2025 | SUPRITI ENTERPRISE | 1424.22 | 65.09 | 4.57 | 30
8 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | Different types of works involve in connection with Augmentation of TEHATA Zone-I & II (SM/16301) Water Supply Scheme, CHAKSIMLA (SM/15586) Water Supply Scheme & DWARIATON (SM/16285) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000162/2024-2025 | 2201/BWD | 13/06/2024 | 05/07/2026 | M/S ASHA CONSTRUCTION | 449.98 | 196.66 | 43.7 | 25
9 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
10 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. | SM/15586 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAK SIMLA Water Supply Scheme [ Block-KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | ASSISTANT ENGINEER | Junior Engineer | ORD/000931/2023-2024 | 4194/CMD | 29/08/2023 | 02/09/2025 | J.S. CONSTRUCTION. | 28.48 | 0 | 0 | 40
Total | [13 empty] | 2052.83 | 262.41 | 12.78