## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | ANGARSON PIPED WATER SUPPLY SCHEME | SM/15587 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 42.44 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | ANGARSON PIPED WATER SUPPLY SCHEME | SM/15587 | New | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.32 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | ANGARSON PIPED WATER SUPPLY SCHEME | SM/15587 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR ANGERSON PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001149/2023-2024 | 2105/KSD | 04/03/2024 | 14/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 99.78 | 2
4 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | ANGARSON PIPED WATER SUPPLY SCHEME | SM/15587 | New | New electric connection for Angarson PWSS, PH-1. |  |  | BILL/01888/2023-2024 | BP-2023-24-349 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.47 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | ANGARSON PIPED WATER SUPPLY SCHEME | SM/15587 | New | New service connection charges for Angarson PWSS TW-2 |  |  | BILL/01865/2023-2024 | BP-2023-24-350 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.07 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | ANGARSON PIPED WATER SUPPLY SCHEME | SM/15587 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | ANGARSON PIPED WATER SUPPLY SCHEME | SM/15587 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | ANGARSON PIPED WATER SUPPLY SCHEME | SM/15587 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at ANGARSON Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000894/2023-2024 | 4157/CMD | 29/08/2023 | 30/05/2025 | S.K. ELECTRICALS | 27.77 | 5.69 | 20.51 | 95
9 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | ANGARSON PIPED WATER SUPPLY SCHEME | SM/15587 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANGARSON, BHABANANDAPUR &DAFARPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000702/2023-2024 | 4480/BWD | 11/10/2023 | 04/10/2025 | M/S GHOSH & CO. | 1093.29 | 186.38 | 17.05 | 75
Total | [13 empty] | 1948.12 | 192.73 | 9.89