## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000517/2023-2024 | 3969/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 28.36 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Work Order for "Route Survey & Prepatration of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-III (Zone-III A) (SM/15588) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-4) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001137/2023-2024 | 2079/KSD | 29/02/2024 | 14/04/2024 | APEX ENGINEERING | 2.27 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000763/2023-2024 | 197/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 6.16 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-3A) with LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000537/2023-2024 | 3701/BWD | 24/08/2023 | 31/12/2025 | SUPRITI ENTERPRISE | 560.35 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 07/02/2026 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Construction of protection wall along with reconstruction of boundary wall (Damaged portion due to land slide along the pond side) and other allied work at Surface Water Based Water Supply Scheme (Zone - 3) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001298/2024-2025 | 913/BWD | 10/03/2025 | 09/04/2025 | MONDAL & CO. | 17.92 | 0 | 0 | 100
Total | [13 empty] | 1824.68 | 0 | 0