## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000517/2023-2024 | 3969/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 28.36 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Work Order for "Route Survey & Prepatration of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-III (Zone-III A) (SM/15588) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-4) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001137/2023-2024 | 2079/KSD | 29/02/2024 | 14/04/2024 | APEX ENGINEERING | 2.27 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000763/2023-2024 | 197/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 6.16 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-3A) with LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000537/2023-2024 | 3701/BWD | 24/08/2023 | 31/12/2025 | SUPRITI ENTERPRISE | 560.35 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | SM/15588 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 07/02/2026 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
Total | [13 empty] | 1806.76 | 0 | 0