## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM | SM/15602 | Augmentation | Laying of HDPE pipes with installation & construction of new valve chambers to control the flow of water within command area of JOUGRAM Piped W/S. Scheme at Jougram habitation, Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000761/2022-2023 | 1292/BWD | 20/03/2023 | 19/04/2023 | DIPAK SARKAR | 18.24 | 18.23 | 99.94 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM | SM/15602 | Augmentation | Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials for JOUGRAM & It's Adjoining Mouzas W/S. scheme under Burdwan Sub-Division, Burdwan Division, P.H.E. Dte. Ref. Drawing No.PC-I/OHR/11/2012 (Sheet No.1&2)(R-I) Dated 20.06.2012. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000020/2021-2022 | 3114/BWD | 02/06/2021 | 29/11/2021 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 90.26 | 90.26 | 100 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM | SM/15602 | Augmentation | Laying of Rising Main with interconnection of OHR and distribution line for JAUGRAM Piped Water Supply Scheme and its adjoining mouzas within Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000763/2022-2023 | 1297/BWD | 21/03/2023 | 20/04/2023 | GOUTAM DEY | 5.55 | 5.54 | 99.86 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM | SM/15602 | Augmentation | Augmentation of JAUGRAM Piped Water Supply Scheme LDS, FHTC, land development, drain at different TW site under JAMALPUR Block, District:- Purba-Bardhaman. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000171/2023-2024 | 3059/BWD | 17/07/2023 | 29/05/2025 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 406.76 | 121.76 | 29.93 | 50
Total | [13 empty] | 520.8 | 235.78 | 45.27