## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-II W/S Scheme at Kalsi Mouza, RASULPUR W/S Scheme at 4th TW site & ALIPUR W/S Scheme at 4th TW site under Memari-I Block under within Burdwan Sub-Division, PHE Dte. [For 3 Nos. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000159/2023-2024 | 2455/BWD | 31/05/2023 | 30/07/2023 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 39.76 | 13.1 | 32.96 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Preparation and Submission of DPR for Augmentation of Rasulpur PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000395/2023-2024 | 1583/BSD | 24/07/2023 | 08/08/2023 | GEO-SOLUTION | 0.78 | 0.77 | 99.01 | 100
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rasulpur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000089/2023-2024 | 2594/CMD | 07/06/2023 | 07/07/2023 | CHOUDHURY ENTERPRISE | 22.76 | 11.08 | 48.69 | 50
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Extension of pipe line and replacing damaged pipe line at Swayerpar Uttar for RASULPUR and its adj.mouza W/S Scheme,Block:Memari-I within Burdwan Sub-Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/001174/2023-2024 | 533/BSD | 14/03/2024 | 13/04/2024 | DEBASHISH ENTERPRISE | 0.93 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Installation of air valve with valve Chamber and installation of pressure gauge for improvement of valve pressure at dist.line,repairing valve chamber with RCC cover slab and interconnection of valve chamber with upvc pipe for draining out waste water at Head work site of RASULPUR PWSS under Memari-I Dev.Block under Bardhaman Sadar south sub-Divn,PHE Dte |  | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000118/2024-2025 | 997/BSD | 06/06/2024 | 06/07/2024 | DEBASHISH ENTERPRISE | 0.83 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Construction of switch rooms & Rising main at different TW site for RASULPUR Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000881/2023-2024 | 5356/BWD | 06/12/2023 | 04/02/2024 | SANDIP SARKAR | 7.43 | 5.45 | 73.35 | 95
7 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Supply & installation of Automatic Chlorinator at Rasulpur water supply scheme, P.H. No.- II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001750/2023-2024 | 18/CMSD | 04/01/2024 | 16/01/2024 | MS S M ELECTRICAL | 0.96 | 0.96 | 100 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Extension of height of Boundary Wall by Angle Rolled Section and Barbed Wire and Roof treatment of Pump house for Rasulpur and its Adjoining Mouza W/S Scheme, block -Memari-I within Burdwan Sub-Division ,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000300/2024-2025 | 1282/BSD | 12/07/2024 | 10/09/2024 | GHOSH CONSTRUCTION | 1.27 | 1.23 | 96.77 | 98
9 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Quotation for New Electric Connection for Rasulpur Augmentation W/S Scheme TW No. - 4 |  |  | BILL/01735/2023-2024 | BP-2023-24-254 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.09 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | SM/15701 | Augmentation | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for RASULPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000982/2024-2025 | 4474/BWD | 19/12/2024 | 19/03/2025 | SARKAR AGENCY | 91.74 | 0 | 0 | 51
Total | [13 empty] | 176.56 | 32.6 | 18.46