## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUENTA | SM/15718 | Augmentation | Pipeline with FHTC for KEUNTA Water Supply Scheme at Kalui village (30 Nos.), Keunta village (30 Nos.), Mandarpur village (30 Nos.), Rampur village (30 Nos.), Nandanpur village (60 Nos.), within Raina-II Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000712/2022-2023 | 855/BWD | 28/02/2023 | 14/04/2023 | DUBE ENTERPRISE | 60.1 | 10.1 | 16.81 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUENTA | SM/15718 | Augmentation | Laying of pipeline due to damage for drainage work at Keunta Piped Water Supply Scheme within Raina-II block under Burdwan Division, PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001503/2024-2025 | 112/BSD | 16/01/2025 | 16/03/2025 | DEBJYOTI GOSWAMI | 3.87 | 0 | 0 | 100
Total | [13 empty] | 63.97 | 10.1 | 15.79