## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | SM/15722 | Augmentation | Preparation and Submission of DPR for Augmentation of Gobindapur PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000366/2023-2024 | 1529/BSD | 17/07/2023 | 01/08/2023 | CARTO | 0.78 | 0.77 | 99.01 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | SM/15722 | Augmentation | Extension of PVC water supply line for GOBINDAPUR and its adjoining Mouza W/S Scheme, Block-Memari-I within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000623/2023-2024 | 3920/BWD | 05/09/2023 | 05/10/2023 | J K CORPORATION | 27.92 | 23.56 | 84.37 | 98
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | SM/15722 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 at Augmentation of GOBINDAPUR Water Supply Scheme [BLOCK- MEMARI-I] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001610/2023-2024 | 1538/CMD | 05/03/2024 | 04/05/2024 | BEHERA ENTERPRISE | 12.33 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | SM/15722 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Ichhabacha village of Memari-I Block under Gobindapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) |  | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000473/2025-2026 | 2338/BSD | 21/08/2025 | 31/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
Total | [13 empty] | 41.75 | 24.33 | 58.27