## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Installation of a voltage Correcting device along with allied accessories at PALASAN Water Supply Scheme, Pump House-1, under CMD, PHE Dte., Dist.- Paschim-Bardhaman. |  |  | ORD/000948/2022-2023 | 1160/CMD | 13/03/2023 | 12/04/2023 | P.K. ENGINEERING | 2.98 | 2.98 | 100 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Palasan Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000206/2023-2024 | 3047/CMD | 20/07/2023 | 19/08/2023 | S.K. ELECTRICALS | 11.09 | 10.23 | 92.22 | 80
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of PALASON & its adjoining mouzas Piped Water Supply Scheme, Block - Raina - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000515/2022-2023 | 4612/BWD | 17/10/2022 | 16/11/2022 | M/S SYCHROTECH INDUSTRY | 10.12 | 8.33 | 82.34 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for PALASON its Adjoining Mouza W/S Scheme, Block - Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- PASCHIM PARA) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000765/2022-2023 | 497/BSD | 21/03/2023 | 05/05/2023 | MAA MAHAMAYA CONSTRUCTION | 3.63 | 3.32 | 91.51 | 100
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | New Service Connection Charges Bill for TW-3 of Aug. Palasan W/S Scheme |  |  | BILL/00571/2023-2024 | BP-2023-24-7 | 08/05/2023 | 08/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.39 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PALASHAN Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000001/2023-2024 | 1601/BWD | 04/04/2023 | 03/06/2023 | BHOWMICK ENTERPRISE | 50.14 | 47.9 | 95.53 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Improvement work of PALASON Piped Water Supply Scheme for smooth running of FHTC within Raina-I block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001195/2023-2024 | 2739/BSD | 28/11/2023 | 28/12/2023 | ANWESHA CONSTRUCTION | 0.95 | 0.94 | 99.17 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at 3rd TW Site and providing leftout FHTC, Road Restoration with allied work for PALASON Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000688/2024-2025 | 3671/BWD | 22/10/2024 | 20/01/2025 | A.K. SIKDAR | 42.74 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/07/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Paschimpara village of Raina-I Block under Palashan Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte(5 nos Board) |  |  | ORD/000514/2025-2026 | 2355/BSD | 21/08/2025 | 31/08/2025 | S.M. ENGOCON | 0.72 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Left out FHTC & distribution Networks at Palasan Paschim para under PALASAN Piped Water Supply Scheme, Block- RAINA-I within Burdwan Sub-Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000781/2025-2026 | 1471/BSD | 25/06/2025 | 25/07/2025 | SK ABDUL HALIM | 1.97 | 0 | 0 | 0
Total | [13 empty] | 439.33 | 73.7 | 16.77