## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Installation of a voltage Correcting device along with allied accessories at PALASAN Water Supply Scheme, Pump House-1, under CMD, PHE Dte., Dist.- Paschim-Bardhaman. |  |  | ORD/000948/2022-2023 | 1160/CMD | 13/03/2023 | 12/04/2023 | P.K. ENGINEERING | 2.98 | 2.98 | 100 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Palasan Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000206/2023-2024 | 3047/CMD | 20/07/2023 | 19/08/2023 | S.K. ELECTRICALS | 11.09 | 10.23 | 92.22 | 80
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of PALASON & its adjoining mouzas Piped Water Supply Scheme, Block - Raina - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000515/2022-2023 | 4612/BWD | 17/10/2022 | 16/11/2022 | M/S SYCHROTECH INDUSTRY | 10.12 | 8.33 | 82.34 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for PALASON its Adjoining Mouza W/S Scheme, Block - Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- PASCHIM PARA) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000765/2022-2023 | 497/BSD | 21/03/2023 | 05/05/2023 | MAA MAHAMAYA CONSTRUCTION | 3.63 | 3.32 | 91.51 | 100
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | New Service Connection Charges Bill for TW-3 of Aug. Palasan W/S Scheme |  |  | BILL/00571/2023-2024 | BP-2023-24-7 | 08/05/2023 | 08/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.39 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PALASHAN Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000001/2023-2024 | 1601/BWD | 04/04/2023 | 03/06/2023 | BHOWMICK ENTERPRISE | 50.14 | 47.9 | 95.53 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Improvement work of PALASON Piped Water Supply Scheme for smooth running of FHTC within Raina-I block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001195/2023-2024 | 2739/BSD | 28/11/2023 | 28/12/2023 | ANWESHA CONSTRUCTION | 0.95 | 0.94 | 99.17 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Paschimpara village of Raina-I Block under Palashan Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte(5 nos Board) |  |  | ORD/000514/2025-2026 | 2355/BSD | 21/08/2025 | 31/08/2025 | S.M. ENGOCON | 0.72 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | SM/15723 | Augmentation | Left out FHTC & distribution Networks at Palasan Paschim para under PALASAN Piped Water Supply Scheme, Block- RAINA-I within Burdwan Sub-Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000781/2025-2026 | 1471/BSD | 25/06/2025 | 25/07/2025 | SK ABDUL HALIM | 1.97 | 0 | 0 | 0
Total | [13 empty] | 86.99 | 73.7 | 84.72