## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME | SM/15725 | Augmentation | Preparation and Submission of DPR for Augmentation of Nandra PWSS under Burdwan-II Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000349/2023-2024 | 1476/BSD | 12/07/2023 | 27/07/2023 | CARTO | 0.78 | 0.77 | 99.01 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME | SM/15725 | Augmentation | Augmentation of NADRA Piped Water Supply Scheme Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & Rising Main under BARDHAMAN-II Block, District:- Purba-Bardhaman. _2ND CALL |  |  | ORD/000965/2023-2024 | 002/BWD | 02/01/2024 | 30/06/2024 | R.G. INFRASTRUCTURE | 72.79 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME | SM/15725 | Augmentation | Continuation Work for the supply of one no. Diesel driven Motor Cab/Maxi Cab (Air Conditioner) on hire basis for the office of the Assistant Engineer, to be used by the Assistant Engineer, RWS Burdwan Sub-Divn., PHE. Dte. (Period from 01/03/2024 to 30/04/2024) |  | Contractual Junior Engineer,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001222/2023-2024 | 62/RWS | 27/02/2024 | 27/04/2024 | MD HASIN | 0.8 | 0.55 | 68.93 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME | SM/15725 | Augmentation | Different type of works related internal pathways and approach road, land development, repair of boundary wall & pump houses and road restoration under NANDRA PWSS under Burdwan II Block under Burdwan Divn., PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000721/2025-2026 | 1404/BWD | 16/05/2025 | 30/06/2025 | POMPA CONSTRUCTION CO. | 5.89 | 0 | 0 | 0
Total | [13 empty] | 80.25 | 1.32 | 1.65