## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM | SM/15753 | Augmentation | Preparation and Submission of DPR for Augmentation of Natungram PWSS under Burdwan-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000347/2023-2024 | 1474/BSD | 12/07/2023 | 27/07/2023 | MEASURE LAND | 0.78 | 0.77 | 99.01 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM | SM/15753 | Augmentation | Augmentation of NATUNGRAM Piped Water Supply Scheme Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & Rising Main under BARDHAMAN-I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000579/2023-2024 | 3726/BWD | 25/08/2023 | 24/08/2024 | BASU ENTERPRISE | 72.82 | 37.76 | 51.86 | 40
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM | SM/15753 | Augmentation | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/07/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM | SM/15753 | Augmentation | Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for NATUNGRAM and KHETIA Piped Water Supply Scheme, Block-Burdwan-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE (RWS) Burdwan-I Block | ORD/001003/2024-2025 | 007/BWD | 02/01/2025 | 01/08/2025 | M/S UNIQUE | 33.59 | 0 | 0 | 80
Total | [13 empty] | 416.78 | 38.53 | 9.25