## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF EKAIHAT PIPED WATER SUPPLY SCHEME | SM/16017 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Ekaihat Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000090/2023-2024 | 2583/CMD | 07/06/2023 | 07/07/2023 | M/S. S.R. ENTERPRISE | 22.38 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF EKAIHAT PIPED WATER SUPPLY SCHEME | SM/16017 | Augmentation | Augmentation of EKAIHAT Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & Construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-I Block, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000174/2023-2024 | 3031/BWD | 14/07/2023 | 01/04/2025 | HAMID SK | 130.08 | 85.39 | 65.65 | 100
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF EKAIHAT PIPED WATER SUPPLY SCHEME | SM/16017 | Augmentation | QUOTATION FOR AUGMENTATION OF EKAIHAT PWSS TW-4 |  |  | BILL/00664/2024-2025 | BP-2024-25-266 | 20/08/2024 | 20/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.65 | 0 | 0 | 0
Total | [13 empty] | 160.11 | 85.39 | 53.33