## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME | SM/16019 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KASIPUR, PATHAR GHATA & SABIDPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000541/2023-2024 | 3697/BWD | 24/08/2023 | 02/10/2025 | SUPRITI ENTERPRISE | 1185.67 | 164.63 | 13.88 | 42
2 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KASIPUR PIPED WATER SUPPLY SCHEME | SM/16019 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KASIPUR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000899/2023-2024 | 4163/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 28.59 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME | SM/16019 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 31.64 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME | SM/16019 | New | Material Requisition To Resource Division |  |  | RTOR000374/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 6.85 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KASIPUR PIPED WATER SUPPLY SCHEME | SM/16019 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
6 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KASIPUR PIPED WATER SUPPLY SCHEME | SM/16019 | New | New service at Kasipur PWSS TW-2. |  |  | BILL/02293/2023-2024 | BP-2023-24-439 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.72 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME | SM/16019 | New | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 10/08/2025 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME | SM/16019 | New | Road restoration work for implementation of KASIPUR PWSS (SM/16019) within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001167/2024-2025 | 559/BWD | 06/02/2025 | 07/05/2025 | SUPRITI ENTERPRISE | 9.43 | 0 | 0 | 100
9 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME | SM/16019 | New | Material Requisition To Resource Division |  |  | RTOR000041/2024-2025 | 321/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 3.11 | 0 | 0 | 0
Total | [13 empty] | 1924.92 | 164.63 | 8.55