## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | MASARU PIPE WATER SUPPLY SCHEME | SM/16020 | New | Material Requisition To Resource Division |  |  | RTOR000341/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.25 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | MASARU PIPE WATER SUPPLY SCHEME | SM/16020 | New | Material Requisition To Resource Division |  |  | RTOR000451/2023-2024 | 3975/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 0.98 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | MASARU PIPE WATER SUPPLY SCHEME | SM/16020 | New | Material Requisition To Resource Division |  |  | RTOR000582/2023-2024 | 4896/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 13.36 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | MASARU PIPE WATER SUPPLY SCHEME | SM/16020 | New | New service connection charges for Mosharu PWSS TW-2 |  |  | BILL/02194/2023-2024 | BP-2023-24-375 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.85 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | MASARU PIPE WATER SUPPLY SCHEME | SM/16020 | New | New service connection charges for Mosharu PWSS TW-1 |  |  | BILL/02195/2023-2024 | BP-2023-24-374 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.41 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | MASARU PIPE WATER SUPPLY SCHEME | SM/16020 | New | MASARU Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 100 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mangalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000495/2023-2024 | 3522/BWD | 10/08/2023 | 02/09/2025 | M/S B.N. GUPTA | 262.74 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | MASARU PIPE WATER SUPPLY SCHEME | SM/16020 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | MASARU PIPE WATER SUPPLY SCHEME | SM/16020 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at MASARU [MONGOLKOTE] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000884/2023-2024 | 4147/CMD | 29/08/2023 | 30/05/2025 | CHOUDHURY ENTERPRISE | 21.27 | 0 | 0 | 46
Total | [13 empty] | 377.52 | 0 | 0