## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 36.67 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | Material Requisition To Resource Division |  |  | RTOR000276/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 22.3 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR SABIDPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001154/2023-2024 | 2150/KSD | 07/03/2024 | 17/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 99.78 | 2
4 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | Quotation for new electric service connection at Sabidpur PH NO.-1 |  |  | BILL/01748/2023-2024 | BP-2023-24-255 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.37 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | New service connection for SABIDPUR PWSS TW-2. |  |  | BILL/02400/2023-2024 | BP-2023-24-502 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.96 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KASIPUR, PATHAR GHATA & SABIDPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000541/2023-2024 | 3697/BWD | 24/08/2023 | 02/10/2025 | SUPRITI ENTERPRISE | 1185.67 | 172.3 | 14.53 | 42
7 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SABIDPUR Water Supply Scheme [ Block- KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001045/2023-2024 | 4193/CMD | 29/08/2023 | 30/08/2025 | M/S. S.R. ENTERPRISE | 27.74 | 0 | 0 | 95
8 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 10/08/2025 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
10 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | SABIDPUR PIPED WATER SUPPLY SCHEME | SM/16021 | New | CONTINUATION ORDER-Hiring of inspection vehicle (Diesel/CNG/LPG Driven) [bearing no. WB41H5741] for supervision of the site for the office of the Assistant Engineer,CMD,PHE,Dte.[w.e.f-01.06.2025 to 31.07.2025][JJM WORKS] | ASSISTANT ENGINEER | Junior Engineer | ORD/000010/2025-2026 | 646/CMSD | 26/05/2025 | 26/07/2025 | PRODYUT GHOSH | 0.8 | 0.39 | 49.11 | 0
Total | [13 empty] | 1942.07 | 173.35 | 8.93