## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SAHAPUR PIPED WATER SUPPLY SCHEME | SM/16022 | Augmentation | New service connection charges for Sahapur PWSS TW-1 |  |  | BILL/01521/2023-2024 | BP-2023-24-187 | 09/10/2023 | 09/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.16 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SAHAPUR PIPED WATER SUPPLY SCHEME | SM/16022 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Sahapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000096/2023-2024 | 2586/CMD | 07/06/2023 | 07/07/2023 | M/S, S.S. ENTERPRISE. | 22.6 | 0 | 0 | 46
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SAHAPUR PIPED WATER SUPPLY SCHEME | SM/16022 | Augmentation | Augmentation of SAHAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & renovation of switch-rooms & boundary walls at different TW site under Katwa-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000132/2023-2024 | 2343/BWD | 22/05/2023 | 19/09/2023 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 137.76 | 0 | 0 | 95
Total | [13 empty] | 163.53 | 0 | 0