## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000533/2023-2024 | 3630/BWD | 21/08/2023 | 01/09/2026 | M/S GOUTAM DAS | 1421.7 | 161.16 | 11.34 | 75
2 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at AMEGERIA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000902/2023-2024 | 4166/CMD | 29/08/2023 | 30/05/2025 | M/S, S.DAS AND ENTERPRISE. | 28.48 | 0 | 0 | 88
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 2.01 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Material Requisition To Resource Division |  |  | RTOR000741/2023-2024 | 5252/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.18 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Material Requisition To Resource Division |  |  | RTOR000772/2023-2024 | 199/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 11.48 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Quotation for new service connection at Amegeria PWSS PH-I. |  |  | BILL/00343/2024-2025 | BP-2024-25-167 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.43 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Quotation for new service connection at Amgoria PWSS TW 2. |  |  | BILL/00445/2024-2025 | BP-2024-25-232 | 30/07/2024 | 30/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of AMEGORIA PWSS under Ketugram-I Block within Katwa Sub-Division under Burdwan Division, PHE Dte. [Period for 03(Three) Months ] [Period 01.01.2026 to 31.03.2026][SL No-07] | Assistant Engineer |  | ORD/001322/2025-2026 | 2240/KTS | 31/12/2025 | 31/03/2026 | ABHA ENTERPRISE | 0.65 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME | SM/16023 | New | Road crossing through metal / concrete road by Jack Push Method for AMEGERIA (SM/16023), ARGUN (SM/16482), CHINISPUR (SM/15170) and KULITIA (SM/15167) PWSS under Ketugram I Development Block under Katwa Sub Division within Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/001311/2024-2025 | 977/BWD | 13/03/2025 | 12/05/2025 | M/S GOUTAM DAS | 39.22 | 0 | 0 | 100
Total | [13 empty] | 1611.08 | 161.16 | 10