## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Central Drilling | MAHULA PIPED WATER SUPPLY SCHEME | SM/16025 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilizing Departmental Machineries for Mahula W/S Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000161/2023-2024 | 1057/CDD | 16/08/2023 | 15/09/2023 | C.M. ENTERPRISE | 16.2 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MAHULA PIPED WATER SUPPLY SCHEME | SM/16025 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 2.27 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MAHULA PIPED WATER SUPPLY SCHEME | SM/16025 | New | Material Requisition To Resource Division |  |  | RTOR000337/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 9.89 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MAHULA PIPED WATER SUPPLY SCHEME | SM/16025 | New | Material Requisition To Resource Division |  |  | RTOR000626/2023-2024 | 4872/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 29.6 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MAHULA PIPED WATER SUPPLY SCHEME | SM/16025 | New | MAHULA Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ketugram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000431/2023-2024 | 3665/BWD | 22/08/2023 | 17/06/2024 | SUJATA CONSTRUCTION | 262.37 | 0 | 0 | 3
6 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME | SM/16025 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME | SM/16025 | New | Quotation for new service connection at Mahula PWSS PH-I. |  |  | BILL/00344/2024-2025 | BP-2024-25-173 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.02 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME | SM/16025 | New | Quotation for new service connection at Mahula PWSS PH-2. |  |  | BILL/00350/2024-2025 | BP-2024-25-172 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.31 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME | SM/16025 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at MAHULA [KETUGRAM-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Driller In-Charge | JUNIOR ENGINEER | ORD/000882/2023-2024 | 4145/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 21.4 | 0 | 0 | 70
Total | [13 empty] | 431.35 | 0 | 0