## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at NAYAPARA [MANGOLKOTE] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000892/2023-2024 | 4155/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 21.36 | 9.69 | 45.36 | 46
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | NAYAPARA Piped Water Supply Scheme (Mini Scheme) with sinking of Tube-well, LDS, Rising Main, drain and internal pathway at different TW site under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000840/2023-2024 | 5121/BWD | 23/11/2023 | 01/03/2025 | HAMID SK | 104.6 | 80.8 | 77.24 | 100
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 0.66 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Material Requisition To Resource Division |  |  | RTOR000353/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 16.93 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
6 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Material Requisition To Resource Division |  |  | RTOR000816/2023-2024 | 297/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 14.5 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | NEW SERVICE CONNECTION FOR NAYAPARA PWSS. |  |  | BILL/02476/2023-2024 | BP-2023-24-532 | 13/02/2024 | 13/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.03 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Sinking of additional tube well, Construction of pump house, Boundary wall, Land development under NAYAPARA PWSS, Katwa Sub-Division, Block- Mongolkote, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001102/2024-2025 | 456/BWD | 21/01/2025 | 02/09/2025 | HI-LIGHT ELECTRONICS | 34.04 | 0 | 0 | 20
9 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Providing Functional House Hold Tap Connection in the left out portion of Nayapara village, adjoining area of Pirtala Colony to declare Swajal Gram under the command area of NAYAPARA PWSS (SM/16026), under Mongolkote Block within Katwa Sub-Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000031/2025-2026 | 1255/BWD | 24/04/2025 | 11/07/2025 | CHANCHAL PAL | 9.38 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Providing Functional House Hold Tap Connection in the left out portion of adjoining area of Kalitala, Nayapara village in order to declare Swajal Gram under the command area of NAYAPARA PWSS (SM/16026), under Mongolkote Block within Katwa Sub-Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000032/2025-2026 | 1254/BWD | 24/04/2025 | 11/07/2025 | BABUL SK | 9.51 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Qtn for new connection at Nayapara PWSS T/W-2 |  |  | BILL/02482/2025-2026 |  | 02/01/2026 | 02/01/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.32 | 0 | 0 | 0
Total | [13 empty] | 291 | 90.48 | 31.09