## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 0.66 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Material Requisition To Resource Division |  |  | RTOR000353/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 16.93 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at NAYAPARA [MANGOLKOTE] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000892/2023-2024 | 4155/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 21.36 | 0 | 0 | 46
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Material Requisition To Resource Division |  |  | RTOR000816/2023-2024 | 297/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 14.5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | NEW SERVICE CONNECTION FOR NAYAPARA PWSS. |  |  | BILL/02476/2023-2024 | BP-2023-24-532 | 13/02/2024 | 13/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.03 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
7 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME | SM/16026 | New | Sinking of additional tube well, Construction of pump house, Boundary wall, Land development under NAYAPARA PWSS, Katwa Sub-Division, Block- Mongolkote, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001102/2024-2025 | 456/BWD | 21/01/2025 | 02/09/2025 | HI-LIGHT ELECTRONICS | 34.04 | 0 | 0 | 20
Total | [13 empty] | 151.18 | 0 | 0