## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 28.1 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Material Requisition To Resource Division |  |  | RTOR000237/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.02 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024]" (Vehicle No-WB 04G 7127) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001248/2023-2024 | 1681/KSD | 22/11/2023 | 23/05/2024 | PARTHA PRATIM ACHARYA | 2.4 | 0.31 | 12.79 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DAFARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001148/2023-2024 | 2104/KSD | 04/03/2024 | 14/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 99.78 | 2
5 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024]" (Vehicle No-WB 04G 7127) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000983/2023-2024 | 1681/KSD | 22/11/2023 | 23/05/2024 | PARTHA PRATIM ACHARYA | 0.87 | 1.57 | 181.11 | 51
6 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | NEW SERVICE CONNECTION FOR DAFARPUR PWSS TW -1. |  |  | BILL/03103/2023-2024 | BP-2023-24-643 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 20.65 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | New service at Dafarpur PWSS TW-2. |  |  | BILL/02292/2023-2024 | BP-2023-24-438 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Additional quotation for Dafarpur PWSS PH-2 |  |  | BILL/00426/2024-2025 | BP-2024-25-224 | 26/07/2024 | 26/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.51 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection Vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.06.2024 to 30.11.2024]" (Vehicle No-WB 04G 7127) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000465/2024-2025 | 272/KSD | 30/05/2024 | 29/11/2024 | PARTHA PRATIM ACHARYA | 2.4 | 1.22 | 50.91 | 0
10 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2024 to 28.02.2025] [Vehicle No-WB 04G 7127]". | Assistant Engineer |  | ORD/001207/2024-2025 | 1877/KSD | 28/11/2024 | 26/02/2025 | PARTHA PRATIM ACHARYA | 1.2 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Continual work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.03.2025 to 31.05.2025] [Vehicle No-WB 04G 7127]". | Assistant Engineer |  | ORD/001450/2024-2025 | 335/KSD | 28/02/2025 | 31/05/2025 | PARTHA PRATIM ACHARYA | 1.2 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Continual work order for " Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01/06/2025 to 31/08/2025] [Vehicle No-WB 04G 7127]". | Assistant Engineer |  | ORD/000329/2025-2026 | 734/KSD | 30/05/2025 | 30/08/2025 | PARTHA PRATIM ACHARYA | 1.2 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at DAFARPUR Water Supply Scheme [Block - KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000895/2023-2024 | 4158/CMD | 29/08/2023 | 31/08/2025 | GOENKA ENTERPRISE | 20.81 | 0 | 0 | 90
Total | [13 empty] | 783.02 | 3.76 | 0.48