## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KASIPUR, PATHAR GHATA & SABIDPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000541/2023-2024 | 3697/BWD | 24/08/2023 | 02/10/2025 | SUPRITI ENTERPRISE | 1185.67 | 122.67 | 10.35 | 42
2 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PATHAR GHATA Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000901/2023-2024 | 4165/CMD | 29/08/2023 | 02/09/2025 | J.S. CONSTRUCTION. | 28.48 | 0 | 0 | 45
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 32.19 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | Material Requisition To Resource Division |  |  | RTOR000368/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 4.93 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | Work Order for "Restoration of pipeline with other allied works at different places of Akalposh, singa, kadiara, panchrakhi mouja under Patahrghata Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-II panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000857/2024-2025 | 1843/KSD | 27/11/2024 | 12/12/2024 | SUPRITI ENTERPRISE | 2.86 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR PATHARGHATA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001167/2023-2024 | 2149/KSD | 07/03/2024 | 17/03/2024 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 99.69 | 100
8 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | New electric connection for Patharghata PWSS, PH-1. |  |  | BILL/01880/2023-2024 | BP-2023-24-351 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.41 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | New electric connection for Patharghata PWSS, PH-2. |  |  | BILL/01879/2023-2024 | BP-2023-24-351 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.33 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME | SM/16029 | New | Material Requisition To Resource Division |  |  | RTOR000039/2024-2025 | 319/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 5.49 | 0 | 0 | 0
Total | [13 empty] | 2032.13 | 123.33 | 6.07