## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | BAKALSA PIPE WATER SUPPLY SCHEME | SM/16030 | New | Material Requisition To Resource Division |  |  | RTOR000221/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 12.89 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | BAKALSA PIPE WATER SUPPLY SCHEME | SM/16030 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAKALSA Water Supply Scheme [ Block- KETUGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | Driller In-Charge | JUNIOR ENGINEER | ORD/000928/2023-2024 | 4191/CMD | 29/08/2023 | 26/12/2024 | MITRA ASSOCIATE | 20.63 | 9.43 | 45.72 | 44
3 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | BAKALSA PIPE WATER SUPPLY SCHEME | SM/16030 | New | New service connection charges for Bakalsa PWSS TW-1 |  |  | BILL/00829/2024-2025 | BP-2024-25-322 | 03/10/2024 | 03/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.62 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | BAKALSA PIPE WATER SUPPLY SCHEME | SM/16030 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bakalsa Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000905/2023-2024 | 4169/CMD | 29/08/2023 | 31/03/2025 | M/S, S.DAS AND ENTERPRISE. | 29.71 | 14.94 | 50.3 | 50
5 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | BAKALSA PIPE WATER SUPPLY SCHEME | SM/16030 | New | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 01/01/2026 | M/S M.M. ENTERPRISE | 205.15 | 6.49 | 3.17 | 65
Total | [13 empty] | 272 | 30.87 | 11.35