## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | KANKURHATI PIPED WATER SUPPLY SCHEME | SM/16031 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KANKURHATI [KETUGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000058/2023-2024 | 2519/CMD | 02/06/2023 | 02/07/2023 | P.K. ENGINEERING | 21.26 | 0 | 0 | 40
2 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME | SM/16031 | New | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 0.87 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME | SM/16031 | New | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 21.7 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME | SM/16031 | New | Material Requisition To Resource Division |  |  | RTOR000564/2023-2024 | 4938/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 0.73 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | KANKURHATI PIPED WATER SUPPLY SCHEME | SM/16031 | New | New service connection charges for Kankurhati W/S Scheme TW-1 |  |  | BILL/00682/2023-2024 | BP-2023-24-28 | 22/06/2023 | 22/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.49 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | KANKURHATI PIPED WATER SUPPLY SCHEME | SM/16031 | New | New service connection charges for Kankurhati PWSS TW-2 |  |  | BILL/01129/2024-2025 | BP-2023-24-406 | 04/12/2024 | 04/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.45 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME | SM/16031 | New | KANKURHATI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at KANKURHATI Mouza (J.L. - 120) under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000791/2022-2023 | 1428/BWD | 24/03/2023 | 31/12/2024 | HAMID SK | 77.54 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME | SM/16031 | New | KANKURHATI Piped Water Supply Scheme (Balance Portion) with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at BEGUNKHOLA Mouza (J.L. - 121) under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/001016/2023-2024 | 517/BWD | 06/02/2024 | 02/10/2025 | OM ENTERPRISE | 60.2 | 0 | 0 | 80
Total | [13 empty] | 191.26 | 0 | 0