## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | SHANKRA PIPE WATER SUPPLY SCHEME | SM/16032 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at SHANKRA [PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000887/2023-2024 | 4150/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 21.22 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME | SM/16032 | New | Material Requisition To Resource Division |  |  | RTOR000305/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 8.59 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME | SM/16032 | New | Material Requisition To Resource Division |  |  | RTOR000590/2023-2024 | 4898/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 13.06 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME | SM/16032 | New | Material Requisition To Resource Division |  |  | RTOR000546/2023-2024 | 4311/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 8.44 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME | SM/16032 | New | Work order for "Service for land acquisition for different PWSS under JJM of Purbasthali-I block under Kalna Sub-Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000962/2023-2024 | 1721/KSD | 05/12/2023 | 05/03/2024 | PARTHA PRATIM ACHARYA | 0.96 | 0 | 0 | 5
6 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME | SM/16032 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000639/2023-2024 | 3957/BWD | 07/09/2023 | 24/07/2026 | M/S B. NANDI | 758.52 | 0 | 0 | 20
7 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | SHANKRA PIPE WATER SUPPLY SCHEME | SM/16032 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 23/02/2025 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
Total | [13 empty] | 864.05 | 0 | 0