## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | LOHARUNDI PIPED WATER SUPPLY SCHEME | SM/16033 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.47 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | LOHARUNDI PIPED WATER SUPPLY SCHEME | SM/16033 | New | Material Requisition To Resource Division |  |  | RTOR000334/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 1.95 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | LOHARUNDI PIPED WATER SUPPLY SCHEME | SM/16033 | New | Material Requisition To Resource Division |  |  | RTOR000562/2023-2024 | 4936/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 0.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | LOHARUNDI PIPED WATER SUPPLY SCHEME | SM/16033 | New | Balance work for extension of pipeline to provide FHTC with land development, plinth protection for pump house under LOHARUNDI PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000572/2024-2025 | 3313/BWD | 06/09/2024 | 05/11/2024 | LAKSHMIKANTA DAS | 9.88 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | LOHARUNDI PIPED WATER SUPPLY SCHEME | SM/16033 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 31/10/2024 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | LOHARUNDI PIPED WATER SUPPLY SCHEME | SM/16033 | New | Quotation for new service connection at Loharudni PWSS PH-2. |  |  | BILL/00347/2024-2025 | BP-2024-25-169 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | LOHARUNDI PIPED WATER SUPPLY SCHEME | SM/16033 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at LOHARUNDI [KETUGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000891/2023-2024 | 4154/CMD | 29/08/2023 | 30/05/2025 | AMUSAR IMPEX PVT. LTD. | 21.26 | 0 | 0 | 46
Total | [13 empty] | 80.34 | 0 | 0