## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | Material Requisition To Resource Division |  |  | RTOR000262/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.84 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | Material Requisition To Resource Division |  |  | RTOR000503/2023-2024 | 4027/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.09 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | Material Requisition To Resource Division |  |  | RTOR000585/2023-2024 | 4929/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 39.66 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at GHUNI [PURBASTHALI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000889/2023-2024 | 4152/CMD | 29/08/2023 | 28/09/2023 | S.K. ELECTRICALS | 20.78 | 18.77 | 90.31 | 90
5 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 31/10/2024 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | work Order "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR GHUNI PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE.". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000565/2024-2025 | 1014/KSD | 07/08/2024 | 22/08/2024 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 99.69 | 100
7 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | NEW SERVICE CONNECTION FOR GHUNI PIPED WATER SUPPLY SCHEME. |  |  | BILL/02829/2023-2024 | BP-2023-24-596 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.04 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | NEW SERVICE CONNECTION FOR |  |  | BILL/02826/2023-2024 | BP-2023-24-595 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GHUNI & JOYKRISHNAPUR Piped Water Supply Scheme under Purbasthali II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000492/2023-2024 | 3510/BWD | 10/08/2023 | 26/10/2025 | BKB INFRA PROJECTS PRIVATE LIMITED | 551.42 | 187.09 | 33.93 | 20
10 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | CONTINUATION ORDER -Hiring of inspection vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant engineer ,under CMD,PHE,Dte. [W.E.F-01/12/2024 to 30/01/2025] [Under JJM Works] | ASSISTANT ENGINEER | Junior Engineer | ORD/000563/2024-2025 | 1377/CMSD | 28/11/2024 | 28/01/2025 | PRODYUT GHOSH | 0.8 | 0.79 | 99.58 | 0
11 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME | SM/16034 | New | Work order for " DESIGNING,MAKING AND ERECTION OF SIGN BOARD FOR SAJAL GRAM IN ¿¿4 No... VILLAGE, ¿PURBASTHALI-II BLOCK UNDER KALNA SUB DIVISION WITHIN BURDWAN DIVISION PHE DTE.(12nos board)". | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000952/2024-2025 | 1985/KSD | 09/12/2024 | 19/12/2024 | OMKAR ENTERPRISE | 1.68 | 0 | 0 | 100
Total | [13 empty] | 690.33 | 207.31 | 30.03