## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | KHARGAKUR PWSS Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000556/2023-2024 | 3751/BWD | 28/08/2023 | 27/08/2024 | MITRA CONSTRUCTION | 310.02 | 161.2 | 52 | 15
2 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHARGAKUR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000893/2023-2024 | 4156/CMD | 29/08/2023 | 28/09/2023 | S.K. ELECTRICALS | 26.96 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | Material Requisition To Resource Division |  |  | RTOR000382/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 14.2 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | Material Requisition To Resource Division |  |  | RTOR000399/2023-2024 | 3842/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 6.91 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | Material Requisition To Resource Division |  |  | RTOR000538/2023-2024 | 4305/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 25.37 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | Quotation for new electric service connection at Khargakur PH NO.-1 |  |  | BILL/01746/2023-2024 | BP-2023-24-257 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.35 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | Quotation for new electric service connection at Khargakur PH NO.-2 |  |  | BILL/01745/2023-2024 | BP-2023-24-256 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.28 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
9 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR KHAGRAKUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001155/2023-2024 | 2171/KSD | 11/03/2024 | 21/03/2024 | MITRA CONSTRUCTION | 0.66 | 0.66 | 99.49 | 100
10 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME | SM/16035 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
Total | [13 empty] | 1152.86 | 161.86 | 14.04