## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | KUSDANGA PWSS Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000706/2023-2024 | 4523/BWD | 12/10/2023 | 02/01/2026 | SYED KHORSED ALAM | 258.8 | 101.31 | 39.14 | 25
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 22.36 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Material Requisition To Resource Division |  |  | RTOR000392/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 10.79 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Material Requisition To Resource Division |  |  | RTOR000632/2023-2024 | 4874/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 28.85 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at KUSDANGA Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001607/2023-2024 | 1536/CMD | 05/03/2024 | 04/05/2024 | MITRA ENTERPRISE | 28.81 | 11.49 | 39.86 | 50
6 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Restoration of Masonary drain due laying of 90 mm. dia. HDPE pipe along with increasing height of boundary wall and other ancillary work under the command area of Kusdanga PWSS (SM/16036) under Kalna Sub Division under Burdwan Divn., PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000885/2024-2025 | 4240/BWD | 03/12/2024 | 24/12/2024 | RUBAL CONSTRUCTION | 13.62 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Road Restoration work under the command area of Kusdanga PWSS (SM/16036) under Kalna Sub Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000886/2024-2025 | 4170/BWD | 29/11/2024 | 20/12/2024 | RUBAL CONSTRUCTION | 15.12 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | NEW SERVICE CONNECTION FOR KUSDANGA PWSS TW -2. |  |  | BILL/03107/2023-2024 | BP-2023-24-647 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.03 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | New Service connection for Kushodanga W/S Scheme. |  |  | BILL/02278/2023-2024 | BP-2023-24-437 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.25 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
Total | [13 empty] | 1070.94 | 112.79 | 10.53