## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 22.36 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Material Requisition To Resource Division |  |  | RTOR000392/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 10.79 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Material Requisition To Resource Division |  |  | RTOR000632/2023-2024 | 4874/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 28.85 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at KUSDANGA Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001607/2023-2024 | 1536/CMD | 05/03/2024 | 04/05/2024 | MITRA ENTERPRISE | 28.81 | 0 | 0 | 50
5 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | New Service connection for Kushodanga W/S Scheme. |  |  | BILL/02278/2023-2024 | BP-2023-24-437 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.25 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | NEW SERVICE CONNECTION FOR KUSDANGA PWSS TW -2. |  |  | BILL/03107/2023-2024 | BP-2023-24-647 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.03 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | KUSDANGA PWSS Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000706/2023-2024 | 4523/BWD | 12/10/2023 | 02/01/2026 | SYED KHORSED ALAM | 258.8 | 0 | 0 | 25
8 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME | SM/16036 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
Total | [13 empty] | 1042.19 | 0 | 0