## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of PALLA W/S Scheme under Memari - I Block within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000203/2023-2024 | 2706/BWD | 08/06/2023 | 08/07/2023 | DAS CONSTRUCTION | 13.26 | 0 | 0 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | Preparation and Submission of DPR for Augmentation of Palla PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000397/2023-2024 | 1585/BSD | 24/07/2023 | 08/08/2023 | MEASURE LAND | 0.78 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | Illumination arrangement & different electro-mechanical works at PALLA and others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000441/2024-2025 | 2798/CMD | 01/10/2024 | 30/11/2024 | SUBRATA BHADRA | 15.45 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augmentation of PALLA[MEMARI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000573/2023-2024 | 3903/CMD | 18/08/2023 | 17/09/2023 | SIMARR | 11.88 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | Construction of switch rooms & Rising main at different TW site for PALLA Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000592/2023-2024 | 3765/BWD | 29/08/2023 | 28/10/2023 | SANDIP SARKAR | 7.52 | 0 | 0 | 98
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | Supply & installation of Automatic Chlorinator at Palla water supply scheme, P.H. No.- II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000243/2024-2025 | 726/CMSD | 10/05/2024 | 20/05/2024 | MITRA ENTERPRISE | 0.96 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | NEW SERVICE CONNECTION FOR PALLA PWSS |  |  | BILL/02597/2023-2024 | BP-2023-24-553 | 20/02/2024 | 20/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.35 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | Additional quotation for installation of DTR 25KVA at Palla PWSS PH-2 |  |  | BILL/00441/2024-2025 | BP-2024-25-235 | 30/07/2024 | 30/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | Augmentation of PALLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Memari - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000099/2023-2024 | 2415/BWD | 29/05/2023 | 29/04/2025 | LAKSHMIKANTA DAS | 11.03 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | SM/16192 | Augmentation | Laying distribution pipe line, FHTC, 3rd tube well installation, Construction of switch room and boundary wall for PALLA village under Augmentation of PALLA Piped Water Supply Scheme, Block - Memari - I, under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000876/2023-2024 | 5329/BWD | 04/12/2023 | 19/04/2025 | SARKAR AGENCY | 136.31 | 0 | 0 | 95
Total | [13 empty] | 209.05 | 0 | 0