## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF PURBASAHAPUR PIPED WATER SUPPLY SCHEME | SM/16193 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of PURBA SAHAPUR[KALNA-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001085/2023-2024 | 4477/CMD | 05/10/2023 | 04/11/2023 | DUTTA ENTERPRISE | 24.4 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASAHAPUR PIPED WATER SUPPLY SCHEME | SM/16193 | Augmentation | Augmentation of PURBA SAHAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - II Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000416/2023-2024 | 3273/BWD | 28/07/2023 | 26/09/2023 | PARTHA PRATIM ACHARYA | 21.94 | 15.27 | 69.59 | 80
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASAHAPUR PIPED WATER SUPPLY SCHEME | SM/16193 | Augmentation | Providing leftout FHTC at different location of Purba Sahapur Mouza under the command area of PURBA SAHAPUR PWSS (SM/16193) in order to declare Purba Sahapur village as Sajalgram under Kalna Sub Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001297/2024-2025 | 912/BWD | 10/03/2025 | 25/03/2025 | SAYAK DEY | 5.79 | 0 | 0 | 100
Total | [13 empty] | 52.13 | 15.27 | 29.29